Sprint 1: Foundation & Shopify Integration (Week 1)

TEODORO - Frontend Lead:

- Set up Next.js project with TypeScript and folder structure

- Configure Shopify Storefront API integration

- Build reusable component library (buttons, cards, navigation components)

- Implement basic routing structure matching the site map

- Create responsive header with navigation (Menu Principal, Zonas, Tienda, etc.)

ULISES - Backend/Content Lead:

- Set up Shopify store backend (products, collections, basic settings)

- Configure Shopify admin and create documentation for client

- Set up authentication flow with Shopify Customer Accounts

- Prepare sample product data and categories

- Create initial deployment pipeline (Vercel/similar)

Client Deliverable: Demo of navigation skeleton + Shopify admin walkthrough session

Sprint 2: Core E-commerce Features (Week 2)

Person 1 - Frontend Lead:

- Build Landing Page with hero section and "Quizá te pueda interesar" recommendations

- Create Product Listing page with filtering/sorting

- Implement Product Detail page (images, videos, "add to cart", "buy now")

- Build Shopping Cart component and page

- Implement 3D dog visualization feature (research library like Three.js/React Three Fiber)

Person 2 - Backend/Integration Lead:

- Integrate Shopify Cart API with frontend

- Set up Shopify Checkout redirect flow

- Configure shipping and payment settings in Shopify

- Implement product search functionality

- Create policies pages (returns, privacy, terms) in Shopify

Client Deliverable: Functional product browsing and cart system

Sprint 3: User Features & Content (Week 3)

Person 1 - Frontend Lead:

- Build User Profile page ("Perfil Usuario")

- Create MVZ (veterinarian) profile section

- Implement appointment booking form ("Agenda tu Consulta")

- Build "¿Quiénes somos?" and "Contáctanos" pages

- Create review submission component

Person 2 - Content/Blog Lead:

- Set up Shopify Blog for news/announcements section

- Create blog listing and detail page templates

- Implement downloadable content section (graphics/resources)

- Configure contact form (email integration or Shopify form app)

- Set up order confirmation email templates in Shopify

Client Deliverable: Complete user journey from browsing to checkout + content management demo

Sprint 4: Polish, Testing & Handoff (Week 4)

Person 1 - Frontend Lead:

- Responsive design refinement (mobile, tablet, desktop)

- Performance optimization (image optimization, lazy loading, code splitting)

- Accessibility audit and fixes (WCAG compliance)

- Cross-browser testing and bug fixes

- SEO optimization (meta tags, structured data)

Person 2 - QA/Documentation Lead:

- End-to-end testing of all user flows

- Create comprehensive Shopify admin documentation for client

- Record video tutorials for product management, blog posting, order processing

- Set up analytics (Google Analytics, Shopify Analytics)

- Final deployment and domain configuration

- Knowledge transfer sessions with client

Client Deliverable: Production-ready site + complete admin documentation + training

Key Considerations:

Why Next.js + Shopify works well:

- Next.js handles custom frontend experience (3D dog, custom layouts)

- Shopify manages products, checkout, inventory, customer accounts

- Clear separation of concerns

Critical Path Items:

- Week 1: Get Shopify API keys and test integration early

- Week 2: Confirm 3D dog feature scope (could be complex)

- Week 3: Ensure appointment booking doesn't conflict with Shopify's customer data

- Week 4: Buffer for unexpected issues

Recommendations:

- Daily standups between Person 1 & 2 (15 min)

- Friday client demos at end of each sprint

- Shopify admin training should start Week 1, not Week 4

- Consider a design system (Tailwind + shadcn/ui) for consistency

- The 3D dog feature might need scoping - is it just a viewer or interactive configurator?

A cambiar antes de la entrega:

- Correo store owner Shopify
- Agregar dominio nuevo a callbacks Headless>Customer API
- Vercel Envs:
Next urls(2), shopify customer callback url, store owner email,